## Week 9 focus
Week 9 progress and next deadlines
Memorial bird feeder. Week 9 status at October 23. Calendar shown: October 19 through November 6.
Prototype and slides due |  | 2026-10-26 |  | MVP due | 2026-11-02
Live presentation: October 26 or October 28, selected at random. Question marks show both possibilities.
Green = complete by the Week 9 cutoff. Gray = remaining target window. Blue = planned work. Exact completion days are not assigned. M = milestone.
MVP work follows review feedback. October 30 is an interim check-in; the improved MVP is due November 2.
V&V protocols must be settled before laboratory collection. The revision and stakeholder contact have no set target.
ID | Task | Responsible | Week 9 status | Scheduled start | Target / end | 2026-10-19T00:00:00.000Z | 2026-10-20T00:00:00.000Z | 2026-10-21T00:00:00.000Z | 2026-10-22T00:00:00.000Z | 2026-10-23T00:00:00.000Z | 2026-10-24T00:00:00.000Z | 2026-10-25T00:00:00.000Z | 2026-10-26T00:00:00.000Z | 2026-10-27T00:00:00.000Z | 2026-10-28T00:00:00.000Z | 2026-10-29T00:00:00.000Z | 2026-10-30T00:00:00.000Z | 2026-10-31T00:00:00.000Z | 2026-11-01T00:00:00.000Z | 2026-11-02T00:00:00.000Z | 2026-11-03T00:00:00.000Z | 2026-11-04T00:00:00.000Z | 2026-11-05T00:00:00.000Z | 2026-11-06T00:00:00.000Z | Kind
Week 9 prototype progress
PR1 | Check approach and refill using the placement drawings | Joe and Ayan; all four | Complete | 2026-10-12 | 2026-10-26 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 4 | [11 empty] | Window
PR2 | Fit the cardboard mockup and check the camera view | Daniel; all four | Complete | 2026-10-14 | 2026-10-26 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 4 | [11 empty] | Window
PR3 | Use camera recognition to control the light and buzzer | Emmett; all four | Complete | 2026-10-14 | 2026-10-26 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 4 | [11 empty] | Window
PR4 | Assess rechargeable power | All four | In progress |  | Unscheduled | [19 empty] | Window
R8 | Resubmit Concept Selection and Gantt chart | All four | Submitted |  | n.a. | [19 empty] | Window
R9 | Revise verification and validation plan | Joe | In progress |  | Unscheduled | [19 empty] | Window
Midterm and MVP
P2 | Prepare midterm slides and individual speaking parts | Ayan and Joseph | In progress | 2026-10-16 | 2026-10-26 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [11 empty] | Window
P3 | Prepare prototype evidence and rehearse the midterm | All four | Rehearsed | 2026-10-19 | 2026-10-26 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [11 empty] | Window
C31 | Midterm slides submission | All four | Planned | 2026-10-26 | 2026-10-26 | [7 empty] | 2 | [11 empty] | Milestone
C11 | Prototypes 1, 2, and 3 | All four | Planned | 2026-10-26 | 2026-10-26 | [7 empty] | 2 | [11 empty] | Milestone
C9 | Midterm Group Presentation | All four | Planned | 2026-10-26 | 2026-10-28 | [7 empty] | 3 |  | 3 | [9 empty] | Either date
C10 | Midterm Individual Presentation Grade | All four | Planned | 2026-10-26 | 2026-10-28 | [7 empty] | 3 |  | 3 | [9 empty] | Either date
I1 | Improve the MVP using midterm review feedback | All four | Planned | 2026-10-29 | 2026-11-02 | [10 empty] | 1 | 1 | 1 | 1 | 1 |  |  |  |  | Window
I2 | Prepare the MVP for repeatable tests | All four | Planned | 2026-10-29 | 2026-11-02 | [10 empty] | 1 | 1 | 1 | 1 | 1 |  |  |  |  | Window
I3 | Record interim MVP progress for the course check-in | All four | Planned | 2026-10-29 | 2026-10-30 | [10 empty] | 1 | 1 | [7 empty] | Window
C14 | Week 10 MVP progress check-in | All four | Planned | 2026-10-30 | 2026-10-30 | [11 empty] | 2 | [7 empty] | Milestone
I4 | Prepare final MVP evidence, short description and roles | All four | Planned | 2026-10-29 | 2026-11-02 | [10 empty] | 1 | 1 | 1 | 1 | 1 |  |  |  |  | Window
M4 | Improved MVP ready for submission | All four | Planned | 2026-11-02 | 2026-11-02 | [14 empty] | 2 |  |  |  |  | Milestone
C13 | MVP (Minimally Viable Prototype) | All four | Planned | 2026-11-02 | 2026-11-02 | [14 empty] | 2 |  |  |  |  | Milestone
Initial laboratory testing
V1 | Collect initial laboratory verification and validation data | All four | Planned | 2026-11-03 | 2026-11-05 | [15 empty] | 1 | 1 | 1 |  | Window
M5 | First laboratory dataset ready | All four | Planned | 2026-11-05 | 2026-11-05 | [17 empty] | 2 |  | Milestone
C16 | Week 11 verification and validation progress check-in | All four | Planned | 2026-11-06 | 2026-11-06 | [18 empty] | 2 | Milestone
Unscheduled stakeholder follow-up
V3 | Arrange the stakeholder follow-up | Joseph | Unscheduled |  | Unscheduled | [19 empty] | Window
Q1 | Propose a window-side view of the enclosure for feedback | Joe | Proposed |  | Unscheduled | [19 empty] | Window
Q2 | Propose a question about computer availability | Joe | Proposed |  | Unscheduled | [19 empty] | Window
Q3 | Propose a question about status visibility from indoors | Joe | Proposed |  | Unscheduled | [19 empty] | Window
V2 | Review fit and usability remotely with the stakeholder | Joseph | Unscheduled |  | Unscheduled | [19 empty] | Window

## Full schedule
Memorial bird feeder schedule
Week 9 status at October 23. Green shading ends at the reporting cutoff; exact completion days are not assigned.
Prototype and slides due |  | 2026-10-26 |  | MVP due | 2026-11-02
Live presentation |  | Oct 26 or Oct 28 |  | After review | 2026-10-29
Green = complete by the Week 9 cutoff. Gray = remaining target window. Blue = planned work. M = milestone. T = scheduled readiness target. ? = possible presentation date.
V&V revision and stakeholder contact remain unscheduled. Field outcomes remain deferred.
The conservative MVP planning window follows the later possible review. Stages can iterate; October 30 is an interim check-in.
Edit common dates on Sources; task dates, owners and status are in this sheet. Fixed course checkpoints do not move automatically.
ID | Task | Responsible | Week 9 status | Scheduled start | Target / end | Days | Needs | Kind | 2026-09-28T00:00:00.000Z | 2026-10-05T00:00:00.000Z | 2026-10-12T00:00:00.000Z | 2026-10-19T00:00:00.000Z | 2026-10-26T00:00:00.000Z | 2026-11-02T00:00:00.000Z | 2026-11-09T00:00:00.000Z | 2026-11-16T00:00:00.000Z | 2026-11-23T00:00:00.000Z | 2026-11-30T00:00:00.000Z | 2026-12-07T00:00:00.000Z | Notes | Related specifications | Source
Concept selection and project documents
R1 | Finalize concept choice and Gantt submission | All four | Complete | 2026-09-28T00:00:00.000Z | 2026-09-28T00:00:00.000Z | 1 |  | Window | 1 | [10 empty] | Completed in the earlier project stages. | All FS / TS | Submitted Gantt
R2 | Define subsystem interfaces and prototype questions | All four | Complete | 2026-09-29T00:00:00.000Z | 2026-10-01T00:00:00.000Z | 3 | R1 | Window | 1 | [10 empty] | Completed in the earlier project stages. | All FS / TS | Submitted Gantt
R3 | Write architecture and three-prototype plan | All four | Complete | 2026-10-02T00:00:00.000Z | 2026-10-05T00:00:00.000Z | 4 | R2 | Window | 1 | 1 | [9 empty] | Completed in the earlier project stages. | All FS / TS | Submitted Gantt
R4 | Define measurable verification and validation methods | All four | Complete | 2026-10-06T00:00:00.000Z | 2026-10-09T00:00:00.000Z | 4 | R3 | Window |  | 1 | [9 empty] | Completed in the earlier project stages. | All FS / TS | Submitted Gantt
R5 | Review and submit verification and validation plan | All four | Complete | 2026-10-12T00:00:00.000Z | 2026-10-12T00:00:00.000Z | 1 | R4 | Window |  |  | 1 | [8 empty] | Completed in the earlier project stages. | All FS / TS | Submitted Gantt
R6 | Revise brainstorming document and resubmit | Joe | Complete | 2026-10-13T00:00:00.000Z | 2026-10-14T00:00:00.000Z | 2 | R1 | Window |  |  | 1 | [9 empty] | All FS / TS | Week 8 log
R7 | Revise architecture and prototype plan and resubmit | Joe | Complete | 2026-10-13T00:00:00.000Z | 2026-10-16T00:00:00.000Z | 4 | R3 | Window |  |  | 1 | [9 empty] | All FS / TS | Week 8 log
R8 | Resubmit Concept Selection and Gantt chart | All four | Submitted |  |  |  | R1 | Window | [11 empty] | The group resubmitted the complete document. | All FS / TS | Week 9 update
R9 | Revise verification and validation plan | Joe | In progress |  |  |  | R5 | Window | [11 empty] | Revision continues. Set a target and settle laboratory protocols before collecting data. | All linked TS | Week 9 update
Prototypes 1 to 3
PR1 | Check approach and refill using the placement drawings | Joe and Ayan; all four | Complete | 2026-10-12T00:00:00.000Z | 2026-10-26 | 15 | R3 | Window |  |  | 1 | 1 | 4 | [6 empty] | The walk-through confirmed the disable, refill and restore sequence. | FS.04–FS.08 | Week 8 and Week 9
PR2 | Fit the cardboard mockup and check the camera view | Daniel; all four | Complete | 2026-10-14T00:00:00.000Z | 2026-10-26 | 13 | PR1 layout | Window |  |  | 1 | 1 | 4 | [6 empty] | Parts fit and the camera view was adequate. The proposed layout, opening and post position were retained. | FS.01, FS.04–FS.08 | Week 9 update
PR3 | Use camera recognition to control the light and buzzer | Emmett; all four | Complete | 2026-10-14T00:00:00.000Z | 2026-10-26 | 13 | PR1 layout; PR2 fit | Window |  |  | 1 | 1 | 4 | [6 empty] | Recognition developed on saved images while the camera was debugged, then camera images controlled both outputs. Accuracy and field performance remain unverified. | FS.01–FS.02; C-DET / C-CTRL | Week 9 update
PR4 | Assess rechargeable power | All four | In progress |  |  |  | PR3 | Window | [11 empty] | Battery powered the bench setup. Runtime, capacity and charging performance remain unverified; no further target is set. | FS.09–FS.10 | Week 8 and Week 9
Midterm and improved MVP
P1 | Order MVP materials and track deliveries | Daniel | Complete | 2026-09-29T00:00:00.000Z | 2026-10-16T00:00:00.000Z | 18 | R1 | Window | 1 | 1 | 1 | [8 empty] | Materials available for the earlier prototype work. | All subsystems | Submitted Gantt
M1 | Prototypes 1 and 2 ready | All four | Complete | 2026-10-26 | 2026-10-26 | 1 | PR1, PR2 | Milestone |  |  |  |  | T | [6 empty] | Prototype work is complete within Week 9. The date is its scheduled readiness target. | All FS / TS | Submitted Gantt
M2 | Prototype 3 ready | All four | Complete | 2026-10-26 | 2026-10-26 | 1 | PR3 | Milestone |  |  |  |  | T | [6 empty] | Camera-image recognition controlled both outputs within Week 9. The date is its scheduled readiness target. | All FS / TS | Submitted Gantt
P2 | Prepare midterm slides and individual speaking parts | Ayan and Joseph | In progress | 2026-10-16T00:00:00.000Z | 2026-10-26 | 11 | PR1–PR3 findings | Window |  |  | 1 | 1 | 1 | [7 empty] | All FS / TS | Submitted Gantt
P3 | Prepare prototype evidence and rehearse the midterm | All four | Rehearsed | 2026-10-19T00:00:00.000Z | 2026-10-26 | 8 | PR1, PR2, PR3 | Window |  |  |  | 1 | 1 | [6 empty] | Rehearsal completed; evidence preparation is scheduled through the submission deadline. | All FS / TS | Submitted Gantt
M3 | Midterm submission package ready | All four | Planned | 2026-10-26 | 2026-10-26 | 1 | P2, P3 | Milestone |  |  |  |  | 2 | [6 empty] | Complete prototype evidence and slides for submission. | All FS / TS | Submitted Gantt
I1 | Improve the MVP using midterm review feedback | All four | Planned | 2026-10-29 | 2026-11-02 | 5 | C9 / C10 review | Window |  |  |  |  | 1 | 1 | [5 empty] | Plan from the later possible review date. The MVP must show improvement beyond the midterm prototype. | All FS / TS | MVP brief; Week 9 dates
I2 | Prepare the MVP for repeatable tests | All four | Planned | 2026-10-29 | 2026-11-02 | 5 | I1 as changes available | Window |  |  |  |  | 1 | 1 | [5 empty] | Use refinement results to define and try a repeatable test for at least one requirement, with data records. | All FS / TS | MVP brief; Week 9 dates
I3 | Record interim MVP progress for the course check-in | All four | Planned | 2026-10-29 | 2026-10-30 | 2 | I1 / I2 progress | Window |  |  |  |  | 1 | [6 empty] | Report improvements available at the interim check-in. Final MVP readiness is a later target. | All FS / TS | Submitted Gantt; Week 9 dates
I4 | Prepare final MVP evidence, short description and roles | All four | Planned | 2026-10-29 | 2026-11-02 | 5 | I1 / I2 findings | Window |  |  |  |  | 1 | 1 | [5 empty] | Include evidence, a 1–2-page description or equivalent, incorporated feedback, remaining risks, next tests and team responsibilities. |  | MVP brief, pp. 1–2
M4 | Improved MVP ready for submission | All four | Planned | 2026-11-02 | 2026-11-02 | 1 | I1, I2, I4 | Milestone | [5 empty] | 2 | [5 empty] | New or improved prototype with core operation and a usable data-collection method. | All FS / TS | MVP brief; Week 9 dates
Verification, validation and stakeholder follow-up
V1 | Collect initial laboratory verification and validation data | All four | Planned | 2026-11-03 | 2026-11-05 | 3 | M4; R9 protocols | Window | [5 empty] | 1 | [5 empty] | Settle V&V protocols first. Collect initial lab data; field seed-loss and bird-feeding outcomes remain deferred. | Lab checks linked to FS / TS | V&V plan; updated MVP date
V2 | Review fit and usability remotely with the stakeholder | Joseph | Unscheduled |  |  |  | V3; current prototype evidence | Window | [11 empty] | Arrange remote review. Actual-site refill, viewing and field performance remain separate tests. | FS.04–FS.06 / linked TS | V&V plan; Week 9 update
V3 | Arrange the stakeholder follow-up | Joseph | Unscheduled |  |  |  | Team review of Q1–Q3 | Window | [11 empty] | No new contact. Raise Q1–Q3 with the team before arranging follow-up. | FS.04–FS.06 | Week 9 update
Q1 | Propose a window-side view of the enclosure for feedback | Joe | Proposed |  |  |  | PR2 | Window | [11 empty] | Show the enclosure/post from the window and ask whether its visibility and position are acceptable. The memorial’s appearance matters. | FS.04, FS.08 | Week 9 follow-up ideas
Q2 | Propose a question about computer availability | Joe | Proposed |  |  |  | PR3 | Window | [11 empty] | Ask whether a computer can stay available when the system runs, or eventual operation must be independent. | Recognition deployment | Week 9 follow-up ideas
Q3 | Propose a question about status visibility from indoors | Joe | Proposed |  |  |  | PR2, PR3 | Window | [11 empty] | The display sits inside the enclosure. Ask how normal, paused and needs-attention states should be visible indoors. | Status / maintenance | Week 9 follow-up ideas
F1 | Field seed-loss, bird-access and actual-site evidence | All four | Deferred |  |  |  | Future field study | Window | [11 empty] | Lab prototypes do not establish seed loss, bird feeding or actual-site refill, viewing and feeder compatibility. | Field and actual-feeder criteria | V&V plan, pp. 1–2, 11–14
M5 | First laboratory dataset ready | All four | Planned | 2026-11-05 | 2026-11-05 | 1 | V1 | Milestone | [5 empty] | 2 | [5 empty] | Initial laboratory dataset for the progress check-in. Remote stakeholder review may still be pending. | All FS / TS | Submitted checkpoint; lab-study scope
V4 | Assemble validation evidence and checkpoint update | Ayan | Planned | 2026-11-06T00:00:00.000Z | 2026-11-09T00:00:00.000Z | 4 | V1; V2 status | Window | [5 empty] | 1 | 1 |  |  |  |  | Present laboratory results and outstanding stakeholder review at the checkpoint. | All linked TS | Submitted Gantt
V5 | Analyze results against targets and document failures | Joseph | Planned | 2026-11-10T00:00:00.000Z | 2026-11-12T00:00:00.000Z | 3 | V4 | Window | [6 empty] | 1 |  |  |  |  | Compare available lab results with targets and record failures. | All linked TS | Submitted Gantt
V6 | Finalize data analysis and improvement priorities | Ayan | Planned | 2026-11-13T00:00:00.000Z | 2026-11-16T00:00:00.000Z | 4 | V5 | Window | [6 empty] | 1 | 1 |  |  |  |  | All FS / TS | Submitted Gantt
V7 | Implement priority fixes and repeat affected tests | All four | Planned | 2026-11-17T00:00:00.000Z | 2026-11-23T00:00:00.000Z | 7 | V6 | Window | [7 empty] | 1 | 1 |  |  |  | Failed TS criteria | Submitted Gantt
M6 | Team milestone: design and test evidence frozen | All four | Planned | 2026-11-23T00:00:00.000Z | 2026-11-23T00:00:00.000Z | 1 | V7 | Milestone | [8 empty] | 2 |  |  |  | All FS / TS | Submitted Gantt
Stakeholder presentation and final deliverables
D1 | Prepare stakeholder MVP presentation materials | Joseph | Planned | 2026-11-17T00:00:00.000Z | 2026-11-19T00:00:00.000Z | 3 | V6 | Window | [7 empty] | 1 |  |  |  |  | All FS / TS | Submitted Gantt
D2 | Draft group report and requirement traceability | Emmett | Planned | 2026-11-16T00:00:00.000Z | 2026-11-25T00:00:00.000Z | 10 | V5 | Window | [7 empty] | 1 | 1 |  |  |  | All FS / TS | Submitted Gantt
D3 | Draft individual reports and contributions | Emmett | Planned | 2026-11-23T00:00:00.000Z | 2026-11-25T00:00:00.000Z | 3 | V6 | Window | [8 empty] | 1 |  |  |  | Individual deliverable | Submitted Gantt
D4 | Review group/individual reports and final evidence | All four | Planned | 2026-11-30T00:00:00.000Z | 2026-12-02T00:00:00.000Z | 3 | M6, D2, D3 | Window | [9 empty] | 1 |  |  | All FS / TS | Submitted Gantt
D5 | Finish reports, CATME and Week 14 log | All four | Planned | 2026-12-03T00:00:00.000Z | 2026-12-04T00:00:00.000Z | 2 | D4 | Window | [9 empty] | 1 |  |  | Course deliverables | Submitted Gantt
M7 | Team milestone: reports ready to submit | All four | Planned | 2026-12-03T00:00:00.000Z | 2026-12-03T00:00:00.000Z | 1 | D4 | Milestone | [9 empty] | 2 |  |  | All FS / TS | Submitted Gantt
D6 | Build final slides and demonstration sequence | Joseph | Planned | 2026-11-30T00:00:00.000Z | 2026-12-04T00:00:00.000Z | 5 | M6 | Window | [9 empty] | 1 |  |  | All FS / TS | Submitted Gantt
D7 | Rehearse group and individual presentation parts | All four | Planned | 2026-12-07T00:00:00.000Z | 2026-12-08T00:00:00.000Z | 2 | D6 | Window | [10 empty] | 1 |  | Course deliverables | Submitted Gantt
M8 | Team milestone: final presentation ready | All four | Planned | 2026-12-08T00:00:00.000Z | 2026-12-08T00:00:00.000Z | 1 | D7 | Milestone | [10 empty] | 2 |  | All FS / TS | Submitted Gantt
D8 | Final presentation delivery / submission | Joseph | Planned | 2026-12-09T00:00:00.000Z | 2026-12-09T00:00:00.000Z | 1 | M8 | Window | [10 empty] | 1 |  | Course deliverables | Submitted Gantt
Weekly project logs
L6 | Maintain and submit Week 6 project log | All four | Complete | 2026-09-28T00:00:00.000Z | 2026-10-02T00:00:00.000Z | 5 |  | Window | 1 | [11 empty] | Course log | Submitted Gantt
L7 | Maintain and submit Week 7 project log | All four | Complete | 2026-10-05T00:00:00.000Z | 2026-10-09T00:00:00.000Z | 5 |  | Window |  | 1 | [10 empty] | Course log | Submitted Gantt
L8 | Maintain and submit Week 8 project log | All four | Complete | 2026-10-12T00:00:00.000Z | 2026-10-16T00:00:00.000Z | 5 |  | Window |  |  | 1 | [9 empty] | Course log | Submitted Gantt
L9 | Maintain and submit Week 9 project log | All four | Prepared | 2026-10-19T00:00:00.000Z | 2026-10-23T00:00:00.000Z | 5 |  | Window |  |  |  | 1 | [8 empty] | Course log | Submitted Gantt
L10 | Maintain and submit Week 10 project log | All four | Planned | 2026-10-26T00:00:00.000Z | 2026-10-30T00:00:00.000Z | 5 |  | Window |  |  |  |  | 1 | [7 empty] | Course log | Submitted Gantt
L11 | Maintain and submit Week 11 project log | All four | Planned | 2026-11-02T00:00:00.000Z | 2026-11-06T00:00:00.000Z | 5 |  | Window | [5 empty] | 1 | [6 empty] | Course log | Submitted Gantt
L12 | Maintain and submit Week 12 project log | All four | Planned | 2026-11-09T00:00:00.000Z | 2026-11-13T00:00:00.000Z | 5 |  | Window | [6 empty] | 1 | [5 empty] | Course log | Submitted Gantt
L13 | Maintain and submit Week 13 project log | All four | Planned | 2026-11-16T00:00:00.000Z | 2026-11-20T00:00:00.000Z | 5 |  | Window | [7 empty] | 1 |  |  |  |  | Course log | Submitted Gantt
L14 | Maintain and submit Week 14 project log | All four | Planned | 2026-11-30T00:00:00.000Z | 2026-12-04T00:00:00.000Z | 5 |  | Window | [9 empty] | 1 |  |  | Course log | Submitted Gantt
Course milestones
C1 | Concept Selection & Gantt Chart | All four | Complete | 2026-09-28T00:00:00.000Z | 2026-09-28T00:00:00.000Z | 1 | R1 | Milestone | 2 | [11 empty] | Course milestone | Submitted Gantt
C2 | Week 6 project log | All four | Complete | 2026-10-02T00:00:00.000Z | 2026-10-02T00:00:00.000Z | 1 | L6 | Milestone | 2 | [11 empty] | Course milestone | Submitted Gantt
C3 | System Architecture and Prototype Plan | All four | Complete | 2026-10-05T00:00:00.000Z | 2026-10-05T00:00:00.000Z | 1 | R3 | Milestone |  | 2 | [10 empty] | Course milestone | Submitted Gantt
C4 | Week 7 Team Progress Check-in: Prototypes 1 and 2 | All four | Complete | 2026-10-09T00:00:00.000Z | 2026-10-09T00:00:00.000Z | 1 | Progress from prototype work | Milestone |  | 2 | [9 empty] | Progress reported while prototype work remained underway. | Course milestone | Submitted Gantt
C5 | Week 7 project log | All four | Complete | 2026-10-09T00:00:00.000Z | 2026-10-09T00:00:00.000Z | 1 | L7 | Milestone |  | 2 | [10 empty] | Course milestone | Submitted Gantt
C6 | Verification and Validation Plan | All four | Complete | 2026-10-12T00:00:00.000Z | 2026-10-12T00:00:00.000Z | 1 | R5 | Milestone |  |  | 2 | [9 empty] | Course milestone | Submitted Gantt
C7 | Week 8 Team Progress Check-in: Prototype 3 | All four | Complete | 2026-10-16T00:00:00.000Z | 2026-10-16T00:00:00.000Z | 1 | Prototype 3 progress | Milestone |  |  | 2 | [8 empty] | Progress reported while prototype work remained underway. | Course milestone | Submitted Gantt
C8 | Week 8 project log | All four | Complete | 2026-10-16T00:00:00.000Z | 2026-10-16T00:00:00.000Z | 1 | L8 | Milestone |  |  | 2 | [9 empty] | Course milestone | Submitted Gantt
C12 | Week 9 project log | All four | Prepared | 2026-10-23T00:00:00.000Z | 2026-10-23T00:00:00.000Z | 1 | L9 | Milestone |  |  |  | 2 | [8 empty] | Course milestone | Submitted Gantt
C31 | Midterm slides submission | All four | Planned | 2026-10-26 | 2026-10-26 | 1 | P2 | Milestone |  |  |  |  | 2 | [6 empty] | Slide submission and live presentation are separate milestones. | Course milestone | Week 9 deadline update
C11 | Prototypes 1, 2, and 3 | All four | Planned | 2026-10-26 | 2026-10-26 | 1 | P3 | Milestone |  |  |  |  | 2 | [7 empty] | Course milestone | Week 9 deadline update
C9 | Midterm Group Presentation | All four | Planned | 2026-10-26 | 2026-10-28 |  | Midterm presentation preparation | Either date |  |  |  |  | 3 | [6 empty] | One of the two listed dates is selected at random. | Course milestone | Week 9 date clarification
C10 | Midterm Individual Presentation Grade | All four | Planned | 2026-10-26 | 2026-10-28 |  | Midterm presentation preparation | Either date |  |  |  |  | 3 | [6 empty] | One of the two listed dates is selected at random. | Course milestone | Week 9 date clarification
C14 | Week 10 MVP progress check-in | All four | Planned | 2026-10-30T00:00:00.000Z | 2026-10-30T00:00:00.000Z | 1 | I3 | Milestone |  |  |  |  | 2 | [6 empty] | Interim progress check-in before final MVP submission. | Course milestone | Submitted Gantt
C15 | Week 10 project log | All four | Planned | 2026-10-30T00:00:00.000Z | 2026-10-30T00:00:00.000Z | 1 | L10 | Milestone |  |  |  |  | 2 | [7 empty] | Course milestone | Submitted Gantt
C13 | MVP (Minimally Viable Prototype) | All four | Planned | 2026-11-02 | 2026-11-02 | 1 | M4 | Milestone | [5 empty] | 2 | [6 empty] | Course milestone | Week 9 deadline update
C16 | Week 11 verification and validation progress check-in | All four | Planned | 2026-11-06T00:00:00.000Z | 2026-11-06T00:00:00.000Z | 1 | M5 | Milestone | [5 empty] | 2 | [5 empty] | Report initial lab results and work that remains. | Course milestone | Submitted Gantt
C17 | Week 11 project log | All four | Planned | 2026-11-06T00:00:00.000Z | 2026-11-06T00:00:00.000Z | 1 | L11 | Milestone | [5 empty] | 2 | [6 empty] | Course milestone | Submitted Gantt
C18 | Validation Testing Checkpoint | All four | Planned | 2026-11-09T00:00:00.000Z | 2026-11-09T00:00:00.000Z | 1 | V4 | Milestone | [6 empty] | 2 |  |  |  |  | Report available evidence and the status of stakeholder review. | Course milestone | Submitted Gantt
C19 | Week 12 Team Progress Check-In: Data Analysis | All four | Planned | 2026-11-13T00:00:00.000Z | 2026-11-13T00:00:00.000Z | 1 | V5 | Milestone | [6 empty] | 2 | [5 empty] | Course milestone | Submitted Gantt
C20 | Week 12 project log | All four | Planned | 2026-11-13T00:00:00.000Z | 2026-11-13T00:00:00.000Z | 1 | L12 | Milestone | [6 empty] | 2 | [5 empty] | Course milestone | Submitted Gantt
C21 | Data Analysis Checkpoint | All four | Planned | 2026-11-16T00:00:00.000Z | 2026-11-16T00:00:00.000Z | 1 | V6 | Milestone | [7 empty] | 2 |  |  |  |  | Course milestone | Submitted Gantt
C22 | Week 13 Team Progress Check-In: Stakeholder MVP Presentation Preparations | All four | Planned | 2026-11-20T00:00:00.000Z | 2026-11-20T00:00:00.000Z | 1 | D1 | Milestone | [7 empty] | 2 |  |  |  |  | Course milestone | Submitted Gantt
C23 | Week 13 project log | All four | Planned | 2026-11-20T00:00:00.000Z | 2026-11-20T00:00:00.000Z | 1 | L13 | Milestone | [7 empty] | 2 |  |  |  |  | Course milestone | Submitted Gantt
C24 | Extra Credit Opportunity: End-of-Semester Course Evaluation | Optional | Optional | 2026-12-04T00:00:00.000Z | 2026-12-04T00:00:00.000Z | 1 |  | Milestone | [9 empty] | 2 |  |  | Course milestone | Submitted Gantt
C25 | Final report | All four | Planned | 2026-12-04T00:00:00.000Z | 2026-12-04T00:00:00.000Z | 1 | M7 | Milestone | [9 empty] | 2 |  |  | Course milestone | Submitted Gantt
C26 | CATME Peer Evaluation | All four | Planned | 2026-12-04T00:00:00.000Z | 2026-12-04T00:00:00.000Z | 1 | D5 | Milestone | [9 empty] | 2 |  |  | Course milestone | Submitted Gantt
C27 | Final report (individual) | All four | Planned | 2026-12-04T00:00:00.000Z | 2026-12-04T00:00:00.000Z | 1 | M7 | Milestone | [9 empty] | 2 |  |  | Course milestone | Submitted Gantt
C28 | Week 14 project log | All four | Planned | 2026-12-04T00:00:00.000Z | 2026-12-04T00:00:00.000Z | 1 | L14 | Milestone | [9 empty] | 2 |  |  | Course milestone | Submitted Gantt
C29 | Final presentation (group) | All four | Planned | 2026-12-09T00:00:00.000Z | 2026-12-09T00:00:00.000Z | 1 | M8 | Milestone | [10 empty] | 2 |  | Course milestone | Submitted Gantt
C30 | Final presentation (individual) | All four | Planned | 2026-12-09T00:00:00.000Z | 2026-12-09T00:00:00.000Z | 1 | M8 | Milestone | [10 empty] | 2 |  | Course milestone | Submitted Gantt

## Sources
Source record and schedule inputs
Input |  | Value |  | Source
Week 9 status date |  | 2026-10-23T00:00:00.000Z |  | Week 9 reporting period
Prototype and slides submission |  | 2026-10-26T00:00:00.000Z |  | Team deadline update
First possible live presentation |  | 2026-10-26T00:00:00.000Z |  | Team schedule clarification
Second possible live presentation |  | 2026-10-28T00:00:00.000Z |  | Random selection; no session assigned
MVP submission |  | 2026-11-02T00:00:00.000Z |  | Team deadline update
MVP progress check-in |  | 2026-10-30T00:00:00.000Z |  | Submitted Gantt, PDF p. 12, C14
V&V progress check-in |  | 2026-11-06T00:00:00.000Z |  | Submitted Gantt, PDF p. 12, C16
Additional sources
Week 8 project log |  | Prototype leads, starts, earlier completion and progress
Week 9 team update |  | Current work, deadlines, resubmission and proposed follow-ups
Verification and Validation Plan |  | Rev B, pp. 1–2 and 11–14. Lab study and deferred field evidence
MVP assignment |  | pp. 1–4 and Canvas rubric. Improvement after review and test readiness
Source conventions |  | All four = Ayan, Daniel, Emmett and Joseph. Blank Complete cells are not completion evidence.
Submitted Gantt baseline
Concept selection and gantt chart.docx.pdf, pp. 9–13. Revision 1, October 12, Daniel Lim. Original printed values below.
ID | Task | Start | Type as printed | End | Days | Predecessors as printed | Specs as printed | Responsible | Complete text | PDF page | Current rows | Reconciliation
R1 | Finalize concept choice and Gantt submission | 2026-09-28T00:00:00.000Z | 28 | 2026-09-28T00:00:00.000Z | 1 | 0 | 0 | All four |  | 9 | R1, R8 | Malformed type/dependency/spec fields corrected in Full schedule.
R2 | Define subsystem interfaces and prototype questions | 2026-09-29T00:00:00.000Z | 29 | 2026-10-01T00:00:00.000Z | 3 | 0 | 2 | All four |  | 9 | R2 | Malformed type/dependency/spec fields corrected in Full schedule.
R3 | Write architecture and three-prototype plan | 2026-10-02T00:00:00.000Z | 2 | 2026-10-05T00:00:00.000Z | 4 | 0 | 3 | All four |  | 9 | R3 | Malformed type/dependency/spec fields corrected in Full schedule.
R4 | Define measurable verification and validation methods | 2026-10-06T00:00:00.000Z | 6 | 2026-10-09T00:00:00.000Z | 4 | 0 | 3 | All four |  | 9 | R4 | Malformed type/dependency/spec fields corrected in Full schedule.
R5 | Review and submit verification and validation plan | 2026-10-12T00:00:00.000Z | 12 | 2026-10-12T00:00:00.000Z | 1 | 0 | 0 | All four |  | 9 | R5 | Malformed type/dependency/spec fields corrected in Full schedule.
S1 | Design seed-loss mechanism and bird clearances | 2026-09-29T00:00:00.000Z | 29 | 2026-10-02T00:00:00.000Z | 4 | 0 | 3 | All four |  | 9 | PR1 | Reconciled to actual prototype sequence; original task completion not inferred.
S2 | Source stock materials and build quick mockup | 2026-10-05T00:00:00.000Z | 5 | 2026-10-07T00:00:00.000Z | 3 | 0 | 2 | Daniel |  | 9 | PR2 | Reconciled to actual prototype sequence; original task completion not inferred.
S3 | Test mockup and capture evidence for check-in | 2026-10-08T00:00:00.000Z | 8 | 2026-10-08T00:00:00.000Z | 1 | 0 | 0 | All four |  | 9 | PR2, F1 | Reconciled to actual prototype sequence; original task completion not inferred.
S4 | Refine seed protection using prototype findings | 2026-10-12T00:00:00.000Z | 12 | 2026-10-16T00:00:00.000Z | 5 | 0 | 4 | All four |  | 9 | PR2, F1 | Reconciled to actual prototype sequence; original task completion not inferred.
W1 | Design rain coverage and drainage paths | 2026-09-29T00:00:00.000Z | 29 | 2026-10-02T00:00:00.000Z | 4 | 0 | 3 | All four |  | 9 | PR2, V1 | Reconciled to actual prototype sequence; original task completion not inferred.
W2 | Build quick weather and drainage mockup | 2026-10-05T00:00:00.000Z | 5 | 2026-10-07T00:00:00.000Z | 3 | 0 | 2 | All four |  | 9 | PR2, V1 | Reconciled to actual prototype sequence; original task completion not inferred.
W3 | Run water tests and record check-in evidence | 2026-10-08T00:00:00.000Z | 8 | 2026-10-08T00:00:00.000Z | 1 | 0 | 0 | All four |  | 9 | V1 | Reconciled to actual prototype sequence; original task completion not inferred.
W4 | Refine rain protection and drainage | 2026-10-12T00:00:00.000Z | 12 | 2026-10-16T00:00:00.000Z | 5 | 0 | 4 | All four |  | 9 | V1 | Reconciled to actual prototype sequence; original task completion not inferred.
A1 | Measure feeder, inscription and window access | 2026-09-29T00:00:00.000Z | Task | 2026-10-02T00:00:00.000Z | 4 | R1 | FS.04–FS.06 | Ayan |  | 9 | PR1 | Reconciled to actual prototype sequence; original task completion not inferred.
A2 | Design removable mounting and service access | 2026-10-05T00:00:00.000Z | 5 | 2026-10-09T00:00:00.000Z | 5 | 0 | 4 | Daniel |  | 9 | PR1 | Reconciled to actual prototype sequence; original task completion not inferred.
A3 | Build mount and rehearse refill/cleaning tasks | 2026-10-12T00:00:00.000Z | 12 | 2026-10-14T00:00:00.000Z | 3 | 0 | 2 | Emmett |  | 9 | PR1 | Reconciled to actual prototype sequence; original task completion not inferred.
A4 | Check visibility, damage and refill clearance | 2026-10-15T00:00:00.000Z | 15 | 2026-10-15T00:00:00.000Z | 1 | 0 | 0 | Joseph |  | 9 | PR1, F1 | Reconciled to actual prototype sequence; original task completion not inferred.
E1 | Define sensing, control states and power needs | 2026-09-29T00:00:00.000Z | Conditional | 2026-10-02T00:00:00.000Z | 4 | R1 | Selected concept TS | All four |  | 10 | PR3 | Reconciled to actual prototype sequence; original task completion not inferred.
E2 | Order parts and develop controller logic | 2026-10-05T00:00:00.000Z | Conditional | 2026-10-09T00:00:00.000Z | 5 | E1 | Selected concept TS | Daniel |  | 10 | PR3 | Reconciled to actual prototype sequence; original task completion not inferred.
E3 | Assemble and bench-test controls and power | 2026-10-12T00:00:00.000Z | Conditional | 2026-10-16T00:00:00.000Z | 5 | E2 | Selected concept TS | All four |  | 10 | PR3 | Reconciled to actual prototype sequence; original task completion not inferred.
E4 | Integrate enclosure, wiring and service mode | 2026-10-19T00:00:00.000Z | Conditional | 2026-10-23T00:00:00.000Z | 5 | E3 | Selected concept TS | All four |  | 10 | PR3 | Reconciled to actual prototype sequence; original task completion not inferred.
P1 | Order MVP materials and track deliveries | 2026-09-29T00:00:00.000Z | Task | 2026-10-16T00:00:00.000Z | 18 | R1 | All subsystems | Daniel |  | 10 | P1 | Retained with current status, scope or date updates where documented.
M1 | Team milestone: Prototypes 1 and 2 ready | 2026-10-08T00:00:00.000Z | Team milestone | 2026-10-08T00:00:00.000Z | 1 | S3, W3 | All FS / TS | All four |  | 10 | M1 | Retained with current status, scope or date updates where documented.
M2 | Team milestone: Prototype 3 ready | 2026-10-15T00:00:00.000Z | Team milestone | 2026-10-15T00:00:00.000Z | 1 | A4 | All FS / TS | All four |  | 10 | M2 | Retained with current status, scope or date updates where documented.
P2 | Prepare midterm slides and individual speaking parts | 2026-10-16T00:00:00.000Z | Task | 2026-10-20T00:00:00.000Z | 5 | M2 | All FS / TS | Ayan and Joseph |  | 10 | P2 | Retained with current status, scope or date updates where documented.
P3 | Package prototype evidence and rehearse midterm | 2026-10-19T00:00:00.000Z | Task | 2026-10-20T00:00:00.000Z | 2 | S4, W4, A4 | All FS / TS | All four |  | 10 | P3 | Retained with current status, scope or date updates where documented.
M3 | Team milestone: midterm package ready | 2026-10-20T00:00:00.000Z | Team milestone | 2026-10-20T00:00:00.000Z | 1 | P2, P3 | All FS / TS | All four |  | 10 | M3 | Retained with current status, scope or date updates where documented.
I1 | Assemble MVP mechanical interfaces | 2026-10-19T00:00:00.000Z | Task | 2026-10-23T00:00:00.000Z | 5 | S4, W4, A4, P1 | All FS / TS | All four |  | 10 | I1 | Retained with current status, scope or date updates where documented.
I2 | Test MVP operation and correct integration faults | 2026-10-26T00:00:00.000Z | Task | 2026-10-27T00:00:00.000Z | 2 | I1; E4 if used | All FS / TS | All four |  | 10 | I2 | Retained with current status, scope or date updates where documented.
M4 | Team milestone: MVP ready for submission | 2026-10-27T00:00:00.000Z | Team milestone | 2026-10-27T00:00:00.000Z | 1 | I2 | All FS / TS | All four |  | 10 | M4 | Retained with current status, scope or date updates where documented.
I3 | Capture MVP evidence and prepare progress check-in | 2026-10-28T00:00:00.000Z | Task | 2026-10-29T00:00:00.000Z | 2 | M4 | All FS / TS | All four |  | 10 | I3 | Retained with current status, scope or date updates where documented.
V1 | Verify seed loss, access and rain performance | 2026-10-29T00:00:00.000Z | Task | 2026-11-05T00:00:00.000Z | 8 | M4, R5 | FS.01–FS.03 / linked TS | All four |  | 10 | V1, F1 | Retained with current status, scope or date updates where documented.
V2 | Validate refill, inscription and upkeep with stakeholder | 2026-10-29T00:00:00.000Z | Task | 2026-11-05T00:00:00.000Z | 8 | M4, R5 | FS.04–FS.06 / linked TS | Joseph |  | 10 | V2 | Retained with current status, scope or date updates where documented.
V3 | Arrange stakeholder testing appointment | 2026-10-19T00:00:00.000Z | Task | 2026-10-23T00:00:00.000Z | 5 | R5 | FS.04–FS.06 | Joseph |  | 10 | V3 | Retained with current status, scope or date updates where documented.
V4 | Complete test evidence and validation checkpoint | 2026-11-06T00:00:00.000Z | Task | 2026-11-09T00:00:00.000Z | 4 | V1, V2 | All linked TS | Ayan |  | 10 | V4 | Retained with current status, scope or date updates where documented.
M5 | Team milestone: first test dataset complete | 2026-11-05T00:00:00.000Z | Team milestone | 2026-11-05T00:00:00.000Z | 1 | V1, V2 | All FS / TS | All four |  | 10 | M5 | Retained with current status, scope or date updates where documented.
V5 | Analyze results against targets and document failures | 2026-11-10T00:00:00.000Z | Task | 2026-11-12T00:00:00.000Z | 3 | V4 | All linked TS | Joseph |  | 11 | V5 | Retained with current status, scope or date updates where documented.
V6 | Finalize data analysis and improvement priorities | 2026-11-13T00:00:00.000Z | Task | 2026-11-16T00:00:00.000Z | 4 | V5 | All FS / TS | Ayan |  | 11 | V6 | Retained with current status, scope or date updates where documented.
V7 | Implement priority fixes and repeat affected tests | 2026-11-17T00:00:00.000Z | Task | 2026-11-23T00:00:00.000Z | 7 | V6 | Failed TS criteria | All four |  | 11 | V7 | Retained with current status, scope or date updates where documented.
M6 | Team milestone: design and test evidence frozen | 2026-11-23T00:00:00.000Z | Team milestone | 2026-11-23T00:00:00.000Z | 1 | V7 | All FS / TS | All four |  | 11 | M6 | Retained with current status, scope or date updates where documented.
D1 | Prepare stakeholder MVP presentation materials | 2026-11-17T00:00:00.000Z | Task | 2026-11-19T00:00:00.000Z | 3 | V6 | All FS / TS | Joseph |  | 11 | D1 | Retained with current status, scope or date updates where documented.
D2 | Draft group report and requirement traceability | 2026-11-16T00:00:00.000Z | Task | 2026-11-25T00:00:00.000Z | 10 | V5 | All FS / TS | Emmett |  | 11 | D2 | Retained with current status, scope or date updates where documented.
D3 | Draft individual reports and contributions | 2026-11-23T00:00:00.000Z | Task | 2026-11-25T00:00:00.000Z | 3 | V6 | Individual deliverable | Emmett |  | 11 | D3 | Retained with current status, scope or date updates where documented.
D4 | Review group/individual reports and final evidence | 2026-11-30T00:00:00.000Z | Task | 2026-12-02T00:00:00.000Z | 3 | M6, D2, D3 | All FS / TS | All four |  | 11 | D4 | Retained with current status, scope or date updates where documented.
D5 | Finish reports, CATME and Week 14 log | 2026-12-03T00:00:00.000Z | Task | 2026-12-04T00:00:00.000Z | 2 | D4 | Course deliverables | All four |  | 11 | D5 | Retained with current status, scope or date updates where documented.
M7 | Team milestone: reports ready to submit | 2026-12-03T00:00:00.000Z | Team milestone | 2026-12-03T00:00:00.000Z | 1 | D4 | All FS / TS | All four |  | 11 | M7 | Retained with current status, scope or date updates where documented.
D6 | Build final slides and demonstration sequence | 2026-11-30T00:00:00.000Z | Task | 2026-12-04T00:00:00.000Z | 5 | M6 | All FS / TS | Joseph |  | 11 | D6 | Retained with current status, scope or date updates where documented.
D7 | Rehearse group and individual presentation parts | 2026-12-07T00:00:00.000Z | Task | 2026-12-08T00:00:00.000Z | 2 | D6 | Course deliverables | All four |  | 11 | D7 | Retained with current status, scope or date updates where documented.
M8 | Team milestone: final presentation ready | 2026-12-08T00:00:00.000Z | Team milestone | 2026-12-08T00:00:00.000Z | 1 | D7 | All FS / TS | All four |  | 11 | M8 | Retained with current status, scope or date updates where documented.
D8 | Final presentation delivery / submission | 2026-12-09T00:00:00.000Z | Task | 2026-12-09T00:00:00.000Z | 1 | M8 | Course deliverables | Joseph |  | 11 | D8 | Retained with current status, scope or date updates where documented.
L6 | Maintain and submit Week 6 project log | 2026-09-28T00:00:00.000Z | Task | 2026-10-02T00:00:00.000Z | 5 |  | Course log | All four |  | 11 | L6 | Retained with current status, scope or date updates where documented.
L7 | Maintain and submit Week 7 project log | 2026-10-05T00:00:00.000Z | Task | 2026-10-09T00:00:00.000Z | 5 |  | Course log | All four |  | 11 | L7 | Retained with current status, scope or date updates where documented.
L8 | Maintain and submit Week 8 project log | 2026-10-12T00:00:00.000Z | Task | 2026-10-16T00:00:00.000Z | 5 |  | Course log | All four |  | 11 | L8 | Retained with current status, scope or date updates where documented.
L9 | Maintain and submit Week 9 project log | 2026-10-19T00:00:00.000Z | Task | 2026-10-23T00:00:00.000Z | 5 |  | Course log | All four |  | 11 | L9 | Retained with current status, scope or date updates where documented.
L10 | Maintain and submit Week 10 project log | 2026-10-26T00:00:00.000Z | Task | 2026-10-30T00:00:00.000Z | 5 |  | Course log | All four |  | 11 | L10 | Retained with current status, scope or date updates where documented.
L11 | Maintain and submit Week 11 project log | 2026-11-02T00:00:00.000Z | Task | 2026-11-06T00:00:00.000Z | 5 |  | Course log | All four |  | 11 | L11 | Retained with current status, scope or date updates where documented.
L12 | Maintain and submit Week 12 project log | 2026-11-09T00:00:00.000Z | Task | 2026-11-13T00:00:00.000Z | 5 |  | Course log | All four |  | 12 | L12 | Retained with current status, scope or date updates where documented.
L13 | Maintain and submit Week 13 project log | 2026-11-16T00:00:00.000Z | Task | 2026-11-20T00:00:00.000Z | 5 |  | Course log | All four |  | 12 | L13 | Retained with current status, scope or date updates where documented.
L14 | Maintain and submit Week 14 project log | 2026-11-30T00:00:00.000Z | Task | 2026-12-04T00:00:00.000Z | 5 |  | Course log | All four |  | 12 | L14 | Retained with current status, scope or date updates where documented.
C1 | Concept Selection & Gantt Chart | 2026-09-28T00:00:00.000Z | Course milestone | 2026-09-28T00:00:00.000Z | 1 | R1 | Course milestone | All four |  | 12 | C1 | Retained with current status, scope or date updates where documented.
C2 | Week 6 project log | 2026-10-02T00:00:00.000Z | Course milestone | 2026-10-02T00:00:00.000Z | 1 | L6 | Course milestone | All four |  | 12 | C2 | Retained with current status, scope or date updates where documented.
C3 | System Architecture and Prototype Plan | 2026-10-05T00:00:00.000Z | Course milestone | 2026-10-05T00:00:00.000Z | 1 | R3 | Course milestone | All four |  | 12 | C3 | Retained with current status, scope or date updates where documented.
C4 | Week 7 Team Progress Check-in: Prototypes 1 and 2 | 2026-10-09T00:00:00.000Z | Course milestone | 2026-10-09T00:00:00.000Z | 1 | M1 | Course milestone | All four |  | 12 | C4 | Retained with current status, scope or date updates where documented.
C5 | Week 7 project log | 2026-10-09T00:00:00.000Z | Course milestone | 2026-10-09T00:00:00.000Z | 1 | L7 | Course milestone | All four |  | 12 | C5 | Retained with current status, scope or date updates where documented.
C6 | Verification and Validation Plan | 2026-10-12T00:00:00.000Z | Course milestone | 2026-10-12T00:00:00.000Z | 1 | R5 | Course milestone | All four |  | 12 | C6 | Retained with current status, scope or date updates where documented.
C7 | Week 8 Team Progress Check-in: Prototype 3 | 2026-10-16T00:00:00.000Z | Course milestone | 2026-10-16T00:00:00.000Z | 1 | M2 | Course milestone | All four |  | 12 | C7 | Retained with current status, scope or date updates where documented.
C8 | Week 8 project log | 2026-10-16T00:00:00.000Z | Course milestone | 2026-10-16T00:00:00.000Z | 1 | L8 | Course milestone | All four |  | 12 | C8 | Retained with current status, scope or date updates where documented.
C9 | Midterm Group Presentation | 2026-10-21T00:00:00.000Z | Course milestone | 2026-10-21T00:00:00.000Z | 1 | M3 | Course milestone | All four |  | 12 | C9 | Retained with current status, scope or date updates where documented.
C10 | Midterm Individual Presentation Grade | 2026-10-21T00:00:00.000Z | Course milestone | 2026-10-21T00:00:00.000Z | 1 | M3 | Course milestone | All four |  | 12 | C10 | Retained with current status, scope or date updates where documented.
C11 | Prototypes 1, 2, and 3 | 2026-10-21T00:00:00.000Z | Course milestone | 2026-10-21T00:00:00.000Z | 1 | P3 | Course milestone | All four |  | 12 | C11 | Retained with current status, scope or date updates where documented.
C12 | Week 9 project log | 2026-10-23T00:00:00.000Z | Course milestone | 2026-10-23T00:00:00.000Z | 1 | L9 | Course milestone | All four |  | 12 | C12 | Retained with current status, scope or date updates where documented.
C13 | MVP (Minimally Viable Prototype) | 2026-10-28T00:00:00.000Z | Course milestone | 2026-10-28T00:00:00.000Z | 1 | M4 | Course milestone | All four |  | 12 | C13 | Retained with current status, scope or date updates where documented.
C14 | Week 10 Team Progress Check-in: MVP | 2026-10-30T00:00:00.000Z | Course milestone | 2026-10-30T00:00:00.000Z | 1 | I3 | Course milestone | All four |  | 12 | C14 | Retained with current status, scope or date updates where documented.
C15 | Week 10 project log | 2026-10-30T00:00:00.000Z | Course milestone | 2026-10-30T00:00:00.000Z | 1 | L10 | Course milestone | All four |  | 12 | C15 | Retained with current status, scope or date updates where documented.
C16 | Week 11 Team Progress Check-in: Verification + Validation Testing | 2026-11-06T00:00:00.000Z | Course milestone | 2026-11-06T00:00:00.000Z | 1 | M5 | Course milestone | All four |  | 12 | C16 | Retained with current status, scope or date updates where documented.
C17 | Week 11 project log | 2026-11-06T00:00:00.000Z | Course milestone | 2026-11-06T00:00:00.000Z | 1 | L11 | Course milestone | All four |  | 12 | C17 | Retained with current status, scope or date updates where documented.
C18 | Validation Testing Checkpoint | 2026-11-09T00:00:00.000Z | Course milestone | 2026-11-09T00:00:00.000Z | 1 | V4 | Course milestone | All four |  | 13 | C18 | Retained with current status, scope or date updates where documented.
C19 | Week 12 Team Progress Check-In: Data Analysis | 2026-11-13T00:00:00.000Z | Course milestone | 2026-11-13T00:00:00.000Z | 1 | V5 | Course milestone | All four |  | 13 | C19 | Retained with current status, scope or date updates where documented.
C20 | Week 12 project log | 2026-11-13T00:00:00.000Z | Course milestone | 2026-11-13T00:00:00.000Z | 1 | L12 | Course milestone | All four |  | 13 | C20 | Retained with current status, scope or date updates where documented.
C21 | Data Analysis Checkpoint | 2026-11-16T00:00:00.000Z | Course milestone | 2026-11-16T00:00:00.000Z | 1 | V6 | Course milestone | All four |  | 13 | C21 | Retained with current status, scope or date updates where documented.
C22 | Week 13 Team Progress Check-In: Stakeholder MVP Presentation Preparations | 2026-11-20T00:00:00.000Z | Course milestone | 2026-11-20T00:00:00.000Z | 1 | D1 | Course milestone | All four |  | 13 | C22 | Retained with current status, scope or date updates where documented.
C23 | Week 13 project log | 2026-11-20T00:00:00.000Z | Course milestone | 2026-11-20T00:00:00.000Z | 1 | L13 | Course milestone | All four |  | 13 | C23 | Retained with current status, scope or date updates where documented.
C24 | Extra Credit Opportunity: End-of-Semester Course Evaluation | 2026-12-04T00:00:00.000Z | Course milestone | 2026-12-04T00:00:00.000Z | 1 |  | Course milestone | Optional |  | 13 | C24 | Retained with current status, scope or date updates where documented.
C25 | Final report | 2026-12-04T00:00:00.000Z | Course milestone | 2026-12-04T00:00:00.000Z | 1 | M7 | Course milestone | All four |  | 13 | C25 | Retained with current status, scope or date updates where documented.
C26 | CATME Peer Evaluation | 2026-12-04T00:00:00.000Z | Course milestone | 2026-12-04T00:00:00.000Z | 1 | D5 | Course milestone | All four |  | 13 | C26 | Retained with current status, scope or date updates where documented.
C27 | Final report (individual) | 2026-12-04T00:00:00.000Z | Course milestone | 2026-12-04T00:00:00.000Z | 1 | M7 | Course milestone | All four |  | 13 | C27 | Retained with current status, scope or date updates where documented.
C28 | Week 14 project log | 2026-12-04T00:00:00.000Z | Course milestone | 2026-12-04T00:00:00.000Z | 1 | L14 | Course milestone | All four |  | 13 | C28 | Retained with current status, scope or date updates where documented.
C29 | Final presentation (group) | 2026-12-09T00:00:00.000Z | Course milestone | 2026-12-09T00:00:00.000Z | 1 | M8 | Course milestone | All four |  | 13 | C29 | Retained with current status, scope or date updates where documented.
C30 | Final presentation (individual) | 2026-12-09T00:00:00.000Z | Course milestone | 2026-12-09T00:00:00.000Z | 1 | M8 | Course milestone | All four |  | 13 | C30 | Retained with current status, scope or date updates where documented.